## Active
SITE NAME | Eklutna Army Site | Old Matanuska Townsite | Eklutna Tailrace | ADFG Goose Bay Former Boat Launch | Goose Bay Nike Site Battery Control Area | Briggs Property | Former Peter's Creek Texaco | BLM Goose Bay Airstrip East End Trespass Shooting Range | Goose Bay Nike Site Launch Facility | ADNR Goose Bay State Game Refuge Creek Dump | Matanuska Maid Block | AmeriGas Petrolane | ADOT & PF Palmer Maintenance Facility | Knik Texaco - 1.5 Mile Knik Rd. | Tesoro Northshore #76 | Tesoro - Sandens Peters Creek | Poleline Road Disposal Site, JBER
CONSIDERED FOR CLOSURE | NO | YES: 2023 report was comprehensive. DEC will review site this fall to determine any requirements before closure | YES: DEC is reviewing site for closure | No | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO
HAZARD ID | 25642 | 4004 | 27750 | 26136 | 25974 | 2597 | 24881 | 26269 | 25355 | 4304 | 26608 | 22894 | 24742 | 23488 | 26295 | 23374 | 940
PROBLEM | Old US Armysite used for supplu and sotrage. Had a number of buildings, storage lots, heli landing pad. Site also has AST's. drum piles. Transformers, dump sites, potential UST | Owner stockpiled numerous hazardous materials/wastes onsite, leading to soil contamination. EPA removal action recently took place. | Man-made channel with misc. solid waste including cars, Fridges, Steel drums, and dumped alongside. | trespass shooting range, dump- lead, possible petroleum | Two 20,000 gallon UST assumed to be resomved when site was demolished, but no documentation was found. Plumes of Diesel and dyed heating oil found in subsurface surrounding former tank locations. | City of Palmer unpermitted dump-site run-off contaminating Briggs property | Former gas station with petroleum contamination. 197.7 tons of soil excavated with no groundwater investigation to date. Current site use unkown | Unauthorized shooting area with bullet casings, and other garbage debris. Lean contamination in the soil | Department of Army Corps of Engineers leased from UA to use as a Nike Missile launch facility. Leaking hazarduos materials, UST's, solvents from building contruction. Acid storage buildings, and transformer enclosures. | military dump, including abestos materials. Landfill with 20-30 transformers allegedly buried. 55 gallon drums with soil staining | Full extent of soil contamination has not been defined. Chromium and arsenic found to be naturally ocurring, but other contaminants are present from past or current use | Leaking in piping b/w UST and fuel dispenser. Stockpiles on site 4 12,000 gallon UST's as well as their piping removed in 1994. | multuple UST's removed and levels of DRO and lead remain at limits of excavation. 45 cubic yds of soil stockpiled on site, but not located on site visit in 2009. | Dispenser and three 6,000 gal gas and a 6,000 gal diesel tank removed with coontamination found in soil. Soil removed and stockpiled, additional contamination in soil UST | Gas station from 1995- 2014. soil and grounwater contamination found during UST system closure assesment work. | Several residential wells found contaminated with gasoline. The source was found to be the Tesoro station. About 250 gallons extracted from recovery wells. | Chlorinated compounds found from attemtps to neutralize chemical warfare identification test kits during 1950's. Chemicals and cluster bombs disposed of on-site.
PRIORITY/RISK | Prioritized | Prioritized | Prioritized | Prioritized | Prioritized | Prioritized | Prioritized | Prioritized | Prioritized | Prioritized | Prioritized | Prioritized | Prioritized | Prioritized | Not Priority | Not Priority | Not Priority
REASON | This has been a site of Priority for years. NVE is working on developing a CA for NALEMP to get funding to address lead contaminated soil. | Site has been prioritized for years, Vne assited in first identifying this site and getting a DBAC. It is now close to closure | DEC is currently in discussion of closing this site after years of trying to adress Solid waste and find funding. It is a recreational fishing area that has been traditionally used | Kyle wrote a thriving communties grant to fund site characterization | Kyle from Knik wrote thriving communities grant, site work will occur in 2026. | Kyle is engaged with this site and it is on a shared invneotry between NVE, Knik, and CCTV | Coordinator contacted the SM because SV revealed that IDW was not properly labeled or sealed | Continue coordinating with Kyle to track site progress | Coordination with Kyle from Knik who is engaging on this site | Confirm and Review Inventory project report report | No database entry with information since 2015, just staff SM changes | ADEC requested a workplan on 2/2024 for additonal work, no other updates. Contact SM | Last ADEC update was 2016, no sampling has occurred and site seems to not be up to date with compliancy | Construction seen on site, coordinator contacted SM to determine if this was allowable site activity & if photos are needed. | Consultant is up to date with reporting and RP is active with the site. Remediation of the site is in progress. | Long term ground water monitoring is ocurring and site is actively being managed compliant to DEC priorities. | land limitation regulations in effect and dec is currently reviewing last submitted document.
ADEC LINK | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/25642 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/4004 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/27750 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/26136 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/25974 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/2597 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/24881 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/26269 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/25355 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/4304 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/26608 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/22894 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/24742 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/23488 | http://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/26295 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/23374 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/940
File # | 2108.38.004 | 2245.38.001 |  | 2226.38.007 | 2226.38.006 | 2245.38.020 | 2106.26.003 | 2226.38.008 | 2226.38.003 | 2226.38.001 | 2245.38.043 | 2245.26.015 | 2245.26.010 | 2265.26.017 | 2265.26.037 | 2112.26.001 | 2102.38.002.01
DATE ADDED TO INVENTORY | N/A |  | 2022? | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STATUS | ACTIVE | ACTIVE | Active | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE
RP / PRP | United States Army | Gerald & Wanda Poirier, Estate of Gerald Poirier | ADF&G | ADF&G |  | City of Palmer | David-McCabe, Dawn Water Co. |  | USACE, DOD & ADNR | ADNR | ?? | Petrolane Gas Service. | ADOT | HARRY H. ROSENCRANS / Texaco | Tesoro Refining and Marketing Company. | Tesoro | USAF
LANDOWNER | NVE? | multiple properties (Block 4 Lots 1, 2, 3, 4, 5, 12, 13, 14, 15; Block 2 Lots 5-15) with multiple owners | ADNR | ADF&G | University of Alaska | Ray Briggs | David-McCabe, Dawn Water Co. | BLM | University of Alaska | ADNR | 7 parcels of land, | Petrolane Gas Service. | ADOT | DOT purchased in 2020 | Tesoro Refining and Marketing Company. |  | USAF
SITE TYPE | ?? | Stockpile/dump site | Petroleum/ Solid waste | unauthorized shooting range / dump |  | dump-site | Petroleum | unauthorized shooting range | LUST, old military site | Dump/ |  | LUST, | LUSE | LUST | LUST | LUST | old military site
COC'S | DRO, GRO, benzene, toulene, BTEX, | petroleum, glycol, lead, solvents, asbestos-containing materials, more | DRO, RRO | Lead, | DRO & several PAH's | PCE | Benzene, GRO, TPH | Lead | Abestos, illegally dumped debris, lead, DRO, RRO, PAH's | Abestos, illegal shooting range- lead, possible petroleum, possible hazardous chemicals | lead, mercury, benzo(a)pyrene, pesticides, Napthalane, GRO, DRO, RRO | BTEX, GRO, DRO, benzene | DRO, Benzene, lead | DRO, GRO, Benzene, BTEX | GRO, DRO, BTEX, xylenes | GRO, DRO, benzene, toulene, xylene | VOC,
DATE OF CONTAMINATION | 1957-1971 |  | Some Cars date back to 1970's | sampled in 2013 and added to database | 2012 sound by USACE site investigation | 1996 - email from landowner w/ compaint of contamination | discovered 1991 |  | 1962-1982 | 1987, listed as hazardous site. Site deactivated in 1982 | 2012 site assesment and added to ADEC database | 1993 | 1997 | 1993-12-20 | 1985-2014 while a gas station | 1986 | 1950-1989
MEDIA IMPACTED | Soil, Groundwater | soil, groundwater | Groundwater, Soil | Soil | Soil, Groundwater? | Groundwater, surface water, wetland | Soil, groundwater? | Soil, | Soil, surface, groundwater. | Soil | Soil, groundwater | Soil, Groundwater | Soil, | Soil, Goundwater | Soil, Groundwater | Soil, Groundwater, drinking water wells. | soil, groundwater, surface
ESTIMATED VOLUME | unknown | unknown | Located in tailrace site documents file : amount of debris and location for clean-up | unknown | unknown | Unknown | unknown | unknown | 248 tons of petroleum-impacted soil and 8,000 gal of water/diesel miture transported off site 2011. 2012 200tons excavated and moved off-site. | unknown | unknown | 150 yds gas and 140 cubic yds of diesel contaminated soil stockpiled on site. Additional contamination in soil. | Unknown | unknown | Unknown |  | Unknown
POTENTIAL EXPOSURE PATHWAYS | dermal absorption, ingestion (surface water, surface water, wild/farmed foods), inhalation (indoor/outdoor air) | dermal absorption, ingestion (surface water, surface water, wild/farmed foods), inhalation (indoor/outdoor air) | Mostly a risk of injury due to being public use recreation area. Ingestion of soil |  | dermal absorption, ingestion (surface water, surface water, wild/farmed foods), inhalation (indoor/outdoor air) | Dermal absorprtion, soil ingestion, inhalation, groundwater ingestion | Ingestion, drinking groundwater |  | Dermal absorprtion, ingestion, inhalation, surface contact |  | ingestion of groundwater, incidental ingestion of soil | Dermal absorprtion, soil ingestion, inhalation, groundwater ingestion | Dermal Absorption, ingestion | dermal absorption, ingestion (surface water, surface water, wild/farmed foods), inhalation (indoor/outdoor air) | Dermal absorprtion, soil ingestion, inhalation, groundwater ingestion | Dermal absorprtion, ingestion, inhalation | Dermal absorprtion, soil ingestion, inhalation, groundwater ingestion
DWW WITHIN 1/4 MILE | Nearby | No | YES | Yes | M | NO | Yes, looks within 1/4 m | Yes | Yes | Yes | No | YES | NO | No | YES | Yes | NO
WELL LINK | https://adec.maps.arcgis.com/apps/mapviewer/index.html?webmap=13ed2116e4094f9994775af9a62a1e85 | N/A | https://adec.maps.arcgis.com/apps/mapviewer/index.html?webmap=13ed2116e4094f9994775af9a62a1e85 | https://adec.maps.arcgis.com/apps/mapviewer/index.html?webmap=13ed2116e4094f9994775af9a62a1e85 | https://adec.maps.arcgis.com/apps/mapviewer/index.html?webmap=13ed2116e4094f9994775af9a62a1e85 | N/A | https://adec.maps.arcgis.com/apps/mapviewer/index.html?webmap=13ed2116e4094f9994775af9a62a1e85 | https://adec.maps.arcgis.com/apps/mapviewer/index.html?webmap=13ed2116e4094f9994775af9a62a1e85 | https://adec.maps.arcgis.com/apps/mapviewer/index.html?webmap=13ed2116e4094f9994775af9a62a1e85 | https://adec.maps.arcgis.com/apps/mapviewer/index.html?webmap=13ed2116e4094f9994775af9a62a1e85 | N/A | https://adec.maps.arcgis.com/apps/mapviewer/index.html?webmap=13ed2116e4094f9994775af9a62a1e85 | N/A | N/A | https://adec.maps.arcgis.com/apps/mapviewer/index.html?webmap=13ed2116e4094f9994775af9a62a1e85 | https://adec.maps.arcgis.com/apps/mapviewer/index.html?webmap=13ed2116e4094f9994775af9a62a1e85 | N/A
POTENTIAL SUBSISTENCE IMPACTS? | Yes | YES | YES | M | NO | Yes | No | M | No | M | Yes? | No | No | No | YES? | M? | NO
MONITORING WELLS | Yes | NO | NO | NO | No | No | NO | NO | YES | NO | Yes | YES | NO | Yes | YES | Yes | Yes
STATUS OF MW | Active |  | N/A | N/A | N/A | N/A | N/A | N/A | Active | N/A | ACTIVE ?? | ACTIVE: 2024 requested more wells | N/A | Active | ACTIVE | old decomissioned, new installed in 2020. Active | ACTIVE : long term monitoring
SITE MANAGER | Matthew Fleetwood | Rebekah Reams | Breanna Mahoney | Bill Occonnell | Juliana Smit | Alena Voigt | Mollie Dwyer | Brittani Mack | Juliana Smit | Janice Wiegers | Breanna Mahoney | Kris Dent | Bill Occonnell | Janice Wiegers | Peter Campbell | Bill Occonnell | Ginna Quesada
SM CONTACT | 907-269-7608 Matthew.fleetwood@alaska.gov | 907-451-2144 rebekah.reams@alaska.gov | 907-269-7503 breanna.mahoney@alaska.gov | 907-269-3057 bill.oconnell@alaska.gov | 907-269-3064 Juliana.smit@alaska.gov | 907-269-7556 alena.voigt@alaska.gov | 907-465-1076 Mollie.dwyer@alaska.gov | 907-262-8205 Brittani.mack@alaska.gov | 907-269-3064 Juliana.smit@alaska.gov | 907-451-2127 janice.weigers@alaska.gov | 907-269-7503 Breanna.mahoney@alaska.gov | 907-262-3411 kris.dent@alaska.gov | 907-269-3057 bill.oconnell@alaska.gov | 907-451-2127 janice.weigers@alaska.gov | 907-262-3412 peter.campbell@alaska.gov | 907-269-3057 bill.oconnell@alaska.gov | 907-451-5960 ginna.quesada@alaska.gov
TRP HISTORY w/ SITE | NVE has obtained funding through NALEMP to perform surveys and cleanup actions for this site. Since 2017, drums, contaminated soils, and various surface debris have been located and removed; 2023- NALEMP project for surface debris cleanup; 2024- submitted funding request for TCE pump and treat cleanup pilot project and solar farm redevelopment at this site (EPA Community Change Grant) SM contact 2025 | Targeted Brownfields Assessment, 2018; Stakeholder meeting 2020; 2023- Multiple meetings w/ EPA, DEC, Borough; EPA testing and removal action underway, surface debris largely removed. 2024- reviewed removal action report from EPA, discussed w/EPA coordinator. Attempted Site Visit, but cut short due to safety concerns (hostile person at site); SMC 2025; | DBAC application, 2022 (awarded); Phase 1 Investigation started; SV 2022; reviewed findings from Phase 1, partial Phase 2; submitted for additional funds to continue characterization work; 2024- joint site visit; review assessment reports. 2025 - SV & funding research | SMC, 2021; SV 2021; SMC, SV w/ ADEC, ADNR, ADOT, and Chickaloon TRP May 2022; 2023- meetings held with DHHS regarding human exopsure risk to lead at site. Followup attempts have gone unanswered. | Inquiry sent to FUDS 2024 | SMC- Jan. 2022; SMC Dec. 2022 (new site manager); SMC 2023 | SMC, 2018; SMC, 2021; SMC, 2024; SMC 2025: SV2025 | CSM, 2019; SMC,SV 2021; SMC, SV May 2022; 2024-SMC, review results of sampling efforts and inquire on plans for site | Updated inventory with most recent database entry | SMC, 2021; SV 2021; SV May 2022; 2024 sent to FUDS | N/A | SMC, 2021; SMC 2022; SMC 2023 | SMC, 2025 | SMC, 2019; SMC, 2021; SMC, 2024 | Updated and input to new inventory. Reviewed corrective action workplan for 2025 & 1st quarter monitoring report. | SMC, 2023; reviewed site 5/3/25 | Updated and input to new inventory. Reviewed ADEC updates
LAST TRP ACTION | Emailed FUDS site manager to request any new information or data from summer site work | Reviewed Time Critical Actiton Removal report and completed newsletter article with update | Site visit | meetings held with DHHS regarding human exopsure risk to lead at site. Followup attempts have gone unanswered. | Reviewed Site database to see if report is avaible yet. | Discussed site updates with TRP Coordinator Kyle from Knik. Reviewed reports he obtained. | Site visit & SM contact | Reviewed Site assesment/waste clean-up report from 2024 | Contnue to coordinate with Kyle from Knik who is engaging on this site | Reviewed DEC database to cehck for Inventory Project report that is expected to be avialable by the end of the year. | Reviewed site database and say no monitoring since 2015, and only udpates are SM staff changes. | Reviewed site information on database and recent updates | Received email from SM and reviewed most revent ADEC SV report. | No new updates on DEC database | Reviewed database and updated invenotry with recent database entries , site is currently in remediation. | added new ADEC database update to inventory | Reviewed database, no new updates.
DATE OF ACTION | 9.19.25 | 8.4.25 | 2025-09-19 | 2023 | 2025-09-19 | 2025-07-21 | 9.5.25 | 2025-09-19 | 2025-09-19 | 2024 | 9.19.25 | 2025-09-19 | 2025-09-23 | 2025-09-19 | 2025-05-04 | 2025-09-19 | 2025-09-19
NEXT PROPOSED ACTION | USACE conducting stage 2 in August. Expect update / report after that | Reach out later this fall to determine if there are any remaining needs for closure after they complete a full review. | Contact SM and determine if Database is correct in saying that DEC is drafting a closure memo and anticipated timeline for review/approval of site closure. | Discuss this site with Richard to see current Progress | Check in late fall of 2025 to see if updated report from summer site work is available, if not contact SM. | Continue talking to Kyle and getting updates from his communication with state, borough, and possible landowner | Mollie Dweyer is expected to reach out with any new information on the site about my report. Continue to monitor database and possibly perform site visit to determine if drums are now properly labeled and sealed. | Contact SM and determine if there is any remediation planned for the site now after the clean-up that was performed. | once study is completed ask for results | Check again in November/December for report to be made public | Reach out to SM and ask for update and current status of site. | Contact Sm to see if Rp ever responded or should be contacted again to monitor existing wells, add additonal Groundwater monitoring wells & vapor investogiations | Keep site in mind for Phase I and Phase II site assesment grants | Reach out to site manager requesting 2025 site characterization workplan to determine when site work will be done. | Continue monitoring site and check database to see if approval for installation of pipelines and drilling of remediation well(and covering it) has been completed before asphalt plant closes | Continue to monitor the database for updates. | Contact SM and determine status of review from draft notice of activity and use limitation for the site.
Site Visits Y/N | No | Yes | No | Yes | Yes | No | NO | Yes | No | NO | No | NO | NO | NO | NO | NO | NO
Reason for SV | Ongoing site work this summer will liekly reveal information. For now site visit is not necessary | To document the site after TCRA was completed and site was cleaned-up | Site visit was recently performed, DEC is reviewing | Knik wrote thriving communities grant, site visit will likely occur in 2026 along with on site training for lead characterization. | Knik wrote thriving communities grant, site work will occur in 2026 so site visit may be helpful | Kyle recently visited the site, is engaged, and can provide information about it's status. | Recent site visit was perfomred and SM was contacted about the IDW onsite. | To verify and assess site impacts | in litigation and need access | waiting for report to be updated on database | Should wait until we contact the SM for additional information | Not Priority | Not Priority | Not Priority | Not Priority | Not Priority | Not Priority
LAST ADEC DATABASE ENTRY | DEC staff completed a site visit on June 25, 2025 at the USACE FUDS Eklutna Army Site located near the Native Village of Eklutna. USACE is conducting a high-resolution site characterization (HRSC) of a TCE/chlorinated solvent plume, a VOC Bioaccumulation, and a VOC delineation at the site. The Eklutna Tribe asked specifically for the VOC Bioaccumulation study looking into the uptake of contaminants of concern into plants used by the tribe, and stage one was completed last week with stage 2 happening in August 2025. CS staff observed the geotechnical soil sample collection and ground water sampling | The EPA and the Matsu Borough completed a removal action at the site. Approximately 50 cubic yards of lead contaminated soil, 30 cubic yards of thallium contaminated soil, drums, asbestos containing material, and 500 cubic yards of solid waste was removed from the site during this removal action. | DEC PM drafting site closure memo and ongoing upper management review/approval process will need to be held. Further, preparing updates in the DEC Exposure Tracking Model for anticipated site closure. | Review site file and respond to inquiry from Chickaloon Village Traditional Council. | DEC conducted a site visit to the Battery Control Area and observed field work taking place, including soil borings being installed and test pits being excavated. | File number issued 2245.38.020. | On this date DEC approved an Additional Site Characterization Activities workplan. The goal of the project is to define the vertical extent of contamination at the site and access potential groundwater contamination. The project activities will consist of advancing four soil borings, collecting soil samples, collecting a drinking water well sample, managing investigation-derived waste (IDW), and reporting. The soil borings will be advanced to a maximum of 75 ft or until field screening samples cease to exhibit signs of contamination. The soil samples will be analyzed for GRO, diesel range organics (DRO), and volatile organic compounds (VOCs). Additionally, the sample interval with the highest PID readings (and/or suspected to be the most contaminated) and the duplicate will be analyzed for polynuclear aromatic hydrocarbons (PAHs). The drinking water sample will be analyzed for ethylene dibromide (EDB), VOCS, and PAHs. | Formal DEC Approval of document: GOOSE BAY AIRSTRIP SITE ASSESSMENT / WASTE CLEAN-UP REPORT. The work covered by this report included successful removal of scattered surface debris, as well as analytical soil sampling. Sampling found three burn areas with petroleum-based contamination (one DRO, two PAHs) above ADEC Method 2 MTGW CULs, multiple samples with lead exceedances of human health based CULs, and one sample with elevated arsenic above background levels. Due to th+e small area of contaminated soils, the report recommends excavation with hand tools followed by confirmation sampling. ADEC notes this approach may be adequate, however, further characterization prior to remediation may be required to ensure any soil removal captures all contamination above applicable CULs. | DEC reviewed and provided comments on the Draft Treatability Study Implementation and Baseline Groundwater Sampling Report, dated August 2025. This report provides an overview of the Treatability Study implementation and baseline groundwater sampling and initial results. This document includes injection well and performance monitoring well installation details, soil sampling details and results, baseline groundwater sampling results, and LactOil and s-mZVI injection data. The purpose of the Treatability Study is to evaluate the effectiveness of enhanced reductive dechlorination and in situ chemical reduction technologies in reducing trichloroethene concentrations at the site and eliminating unacceptable risk identified during the Remedial Investigation. | DEC checked with the Army Corps of Engineers, Formerly Used Defense Sites (FUDS) program. FUDS is completing the Inventory Project Report (INPR) but was delayed by the availability of geospatial data. That information was received in December and the report will be submitted this year. | Site transferred to Marc Thomas. | A new workplan request was sent to the RP requesting additional groundwater monitoring wells as well as soil and vapor investigations and to monitor the existing wells to delineate soil and groundwater. | Send letter on this day with brief site history and to outline existing data gaps that need to be addressed before this site could be considered for closure. | Contacted by the consultant, RSE, to discuss slight relocation of one monitoring well to avoid the bike path, and to complete discussion regarding DEC's comments to the workplan. DEC approved the final approach by email. | The consultant (Stantec) sent an email detailing the drilling of a remediation well and the need to finish the installation of the underground recirculation line and cover it this year before the asphalt plant closes. Authorized the installation of the pipelines before receiving a report on the well installation with the assurance that documentation will be forthcoming. | Reviewed sampling memo for 2025 groundwater monitoring at Sandens Tesoro. Samples were collected from MW1, MW2, MW8, MW11, and MW12. MW9 and VES-1 were dry. Contaminants exceeded the cleanup level only in MW2 with GRO up to 5.4 mg/l. | DEC received a Draft Notice of Activity and Use Limitation for JBER-R Site CG039-Poleline Rd Disposal Area (OUB) on this date and is conducting a review.
DATE OF LAST ENTRY | 2025-06-25 | 2023-10-25 | 2025-07-22 | 2025-03-21 | 2025-06-03 | 2004-07-20 | 2025-06-06 | 2024-06-17 | 2025-08-20 | 2025-02-14 | 2021-12-15 | 2024-02-13 | 2016-11-04 | 2025-05-01 | 2025-09-11 | 2025-09-16 | 2025-01-27
ACREAGE | No YES: 22 ?
ADDRESS | Eklutna Village Road, Chugiak, AK 99567 | East D Street and, South 2nd Street, Palmer, AK 99645 | 13145 S. Old Glenn Highway, Palmer, AK 99645 | South of Goose Bay Air Strip on Goose Bay, Big Lake, AK 99652 | Cameo Drive; NW of W End of Goose Bay Airstrip, ~10 Miles SSW of Big Lake, Big Lake, AK 99652 | ~Mile 17 Old Glenn Hwy., Palmer, AK 99645 | 20943 Bill Stephens Drive, Chugiak AK 99567 | East End of Goose Bay Airstrip, Big Lake, AK 99652 | Mile 20 Knik Road, Goose Bay, Big Lake, AK 99652 | Goose Bay NIKE Site Access Road - Cameo Drive, Near the end of Goose Bay Knik Road, Big Lake, AK 99652 | 325 E Dahlia Avenue, Palmer, AK 99645 | 6951 East Blue Lupine Drive, Mile 36.5 Parks Highway, Palmer, AK 99645 | 289 Springer Loop Rd., Palmer, AK 99645 | Mi. 1.5 Knik Rd.; 1800 Goose Bay Road, Wasilla, AK 99687 | 3600 E. Palmer-Wasilla Highway, Wasilla, AK 99654 | 21133 Old Glenn Hwy.; Mi. 22.5 Old Glenn Hwy., Chugiak, AK 99567 | Poleline Rd. & Barrs Blvd FTRS-39, Formerly Fort Richardson before 10/01/2010, Fort Richardson (JBER), AK 99505
BOROUGH | Municipality of Anchorage | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna |  | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Kenai Peninsula
LATITUDE | 61.4588 | 61.5413 | 61.4771 | 61.3923 | 61.3963 | 61.6043 | 61.4092 | 61.3939 | 61.4061 | 61.398 | 61.6005 | 61.5637 | 61.5855 | 61.5631 | 61.5844 | 61.4109 | 61.3036
LONGITUDE | -149.3807 | -149.2274 | -149.1618 | -149.847 | -149.858 | -149.0832 | -149.4466 | -149.8309 | -149.8842 | -149.8669 | -149.1096 | -149.2753 | -149.1199 | -149.46 | -149.3586 | -149.443 | -149.6112
CONSIDERED FOR DBAC | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP | Likely not Eligible: There is a RP
OVERLAP W/ CVTC? | YES NO: YES; YES NO: YES; M NO: YES; M NO: YES; Yes? Yes: YES
OVERLAP W/ KNIK? | NO | YES | YES | YES |  | NO | NO | NO | YES | YES | YES | NO |  | YES | NO |  | NO
*See DEC database entry for full details
Response Action codes
RP | Yes Yes: Responsible Party
SV | Yes Yes: Site Visit
SM | Yes Yes: Site Manager
SMC | Yes Yes: Site Manager Contact
CSM | Yes Yes: Conceptual Site model
ESM | Yes Yes: Ecological Scoping Model

## Clean Up Complete
SITE NAME | Former Four Corners Country Store | Palmer Tesoro AKA Tesoro Fisher Wholesale Tanks | Fishhook Food Mart | Lawn Ranger Illegal Dumping - Eldorado dr. | City of Palmer Public Works Equipment Yard
HAZARD ID | 22961 | 23764 | 26699 | 26479 | 23482
PROBLEM | UST caused soil and groundwater contamination | leaks from UST's on site that is an retired operating commercial fueling station . Remediation underway via land farming | leaks from UST's contaminated soil. Two soil stockpiles on-site. | illicit dump-site in low marshy wetland. Stockpile of unknown origin. Levels exceeded migration to groundwater levels, but could be based on the characteristics of the soil | leak from UST tanks causing soil contamination.
PRIORITY | Not Priority | Not Priority | Not Priority | Not Priority | Not priority
Reason | Series of MW amples resulted in concentrations of contaminated below clean-up levels. Closed in 2019 with recent regulations | Groundwater monitoring resulted in consecuatinve sample below celan-up levels and site is closed. | Soil was treated at a landfarm site and detected Toulene and Xylenes below clean-up levels. | Site was closed 2024, with most recent and up to date closure requirements | Site was closed after a full investigation, 2019. Regulations were up to date. De-prioritization b/c no concentrations above migration to groundwater celan-up levels.
ADEC LINK | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/22961 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/23764 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/26699 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/26479 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/23482
FILE # | 2245.26.004 | 2245.26.002 | 2265.26.039 | 2265.38.042 | 2245.26.009
DATE ADDED TO INVENTORY | N/A | N/A | N/A | N/A | N/A
STATUS | Clean-up complete | Clean-up complete | Clean-up complete | Clean-up complete | Clean-up complete
RP / PRP | Marvin Roofe estate | FISHERS FUEL INC. |  | Lawn Ranger of Alaska, LLC | City of Palmer
LANDOWNER | Marvin Roofe estate | FISHERS FUEL INC. |  | Lawn Ranger of Alaska, LLC | City of Palmer
SITE TYPE | LUST | LUST | LUST | dump-site | LUST
COC'S | BTEX, GRO DRO | VPH, BTEX, DRO, GRO, Benzene | Benzene, GRO, Toulene, Napthalene, | DRO | BTEX, GRO
DATE OF CONTAMINATION | 1993 | 1989 | 2007-2016 | 2015 | tanks removed and contamination found 1991
MEDIA IMPACTED | Soil, Goundwater | Soil | Soil | soil, marshy wetland | Soil
ESTIMATED VOLUME | 200 cubic yds of contaminated soil stockpiled | UNKNOWN | 2 x 10,000 gal UST's and piping- leaked into soil | unknown | 3 x 1,500 gal UST's
POTENTIAL EXPOSURE PATHWAYS | contamination levels below migration to groundwater. Ingestion of soil | contamination levels below migration to groundwater. Ingestion of soil | Ingestion of stockpiled soil | Dermal absorprtion, soil ingestion, inhalation, groundwater ingestion | contamination levels below migration to groundwater. Ingestion of soil
DWW WITHIN 1/4 MILE | NO | YES | YES | NO | NO
WELL LINK | N/A | https://adec.maps.arcgis.com/apps/mapviewer/index.html?webmap=13ed2116e4094f9994775af9a62a1e85 | https://dec.alaska.gov/DWW/JSP/WaterSystemDetail.jsp?tinwsys_is_number=4439&tinwsys_st_code=AK&wsnumber=AK2220029%20%20%20 | N/A | N/A
POTENTIAL SUBSISTENCE IMPACTS? | NO | NO | NO | NO | NO
MONITORING WELLS | YES | YES | NO | NO | NO
STATUS OF MW | UNKNOWN | UNKNOWN | N/A | N/A | N/A
SITE MANAGER | Bill Occonnell | IC unit | IC unit | IC unit | IC unit
SM CONTACT | 907-269-3057 bill.oconnell@alaska.gov | 907-465-5229 dec.icunit@alaska.gov | 907-465-5229 dec.icunit@alaska.gov | 907-465-5229 dec.icunit@alaska.gov | 907-465-5229 dec.icunit@alaska.gov
TRP History with Site | Closure Decision review 6/23 |  | Closure Decision review 6/23 | SMC 2021; | Review Closure Decision- completed, 2/2022
LAST TRP ACTION | Closure Decision review | no history listed. Review closure documents and input in new inventory
DATE OF ACTION | 2023-06-01 | 2025-05-04 | 2023-06-01 | 2021 | 2022-02-01
LAST ADEC DATABASE ENTRY | The Alaska Department of Environmental Conservation (ADEC) has reviewed the environmental records for the Former Four Corners Country Store, located at Mile 4.5 Palmer-Wasilla Highway in Palmer, Alaska. Based on the information provided to date, it has been determined that the contaminants remaining on site do not pose an unacceptable risk to human health or the environment and no further remedial action will be required unless new information becomes available that indicates residual contaminants may pose an unacceptable risk. | Reviewed field work summary for property development activities at Former Palmer Tesoro site. Activities included stockpile sampling, contaminated soil excavation and limited delineation. Stockpiles and excavated soils contained contaminants above DEC cleanup levels and were hauled to the Sutton Hilltop Landfarm for treatment. Confirmation samples from the base and sidewalls of the excavation contained petroleum, contaminants at concentrations consistent with historical data. Contaminant concentration exceeded the migration to groundwater cleanup levels in several locations but were below human health cleanup levels. At the location with the highest results, a test pit was excavated an additional 6 feet below the base of the excavation to evaluate the vertical extent of contamination. A soil sample from the test pit did not contain detectable concentrations of contaminations. This data, along with the existing groundwater data from the site indicates contaminants detected at the base of the excavation are not a risk to groundwater, therefore no further action will be required in these areas. | The Alaska Department of Environmental Conservation, Contaminated Sites Program (ADEC) has completed a review of the environmental records associated with the Fishhook Food Mart located near Wasilla, Alaska. Based on the information provided to date, it has been determined that the contaminant concentrations remaining on site do not pose an unacceptable risk to human health or the environment and no further remedial action will be required unless new information becomes available that indicates residual contaminants may pose an unacceptable risk. | Based on a review of the environmental record, analytical results indicate detectable concentrations for Diesel Range Organics (DRO) remain in the soil at concentrations between 26.4 mg/kg and 36.3 mg/kg. These results are below ADEC Method Two Soil Cleanup Levels in 18 AAC 75.341 Tables B1 and B2 and ADEC has determined that residual contaminant concentrations meet the human health cumulative risk criteria for residential land use. | ADEC sent a letter closing the site based on the results of the 2019 release investigation.
DATE OF LAST ENTRY | 2019-05-15 | 2019-06-28 | 2018-08-17 | 2024-06-28 | 2020-10-22
ACREAGE | unknown | unknown | unknown | unknown | unknown
ADDRESS | Mi. 4.5 Palmer Wasilla Hwy, Palmer, AK 99645 | 174 W Arctic Avenue & Glenn Hwy, Palmer, AK 99645 | 3051 N Wasilla-Fishhook Road; At Intersection w/ E Seldon Road, Wasilla, AK 99654 | Eldorado Drive, Wasilla, AK 99654 | 1316 South Bonanza, Palmer, AK 99645
BOROUGH | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna
LATITUDE | 61.599 | 61.607 | 61.6142 | 61.6398 | 61.5916
LONGITUDE | -149.2492 | -149.1175 | -149.3951 | -149.3485 | -149.1142
OVERLAP W/ CVTC?
OVERLAP W/ KNIK?

## IC's
SITE NAME | Circle S Grocery Store | Peter's Creek Chevron | AAA Transmission Exchange, former Chugiak Texaco | ADOT Knik River Rest Stop, AKA Reflections Lake | ADNR Cottonwood Creek, former Shooting Range | Birchwood Trespass Shooting Area | ADOT & PF Birchwood Maintanence Station Class V Injection Well | JBER-ft. Richardson OUC OB/OD Area
HAZARD ID | 24797 | 26123 | 23983 | 3327 | 25709 | 25757 | 26242 | 431
FILE # | 2106.26.004 | 2106.26.015 | 2106.26.002 | 2245.38.007 | 2265.38.039 | 2106.38.010 | 2106.38.011 | 2102.38.003
PROBLEM | Gasoline and Diesel tanks leaked and contaminated a DWW | Leak from around sumps for underground storage tanks. | Contamination from leaking (diesel) above and underground (Gasoline) storage tanks from previous gas station | previously a shooting range which led to lead contamination in soil | Unauthorized (public) shooting activities leading to lead contamination in soil. | Lead contamination in soil up to 17,000 mg/kg. Being proposed to be developed into a authorized shooting range for law enforcement | Maintanence station from 1980's with 7 floor drains emptied into the class V injection well. Excavation of well and surrounding soils found DRO and RRO contamination | Important staging ground for numerous species, large scale waterfowl mortality notice
PRIORITY | Prioritized | Prioritized | Prioritized | Prioritized | Prioritized | Not Priority | Not Priority | Not Priority
REASON | Ic's can be easily visualized from the car, so it is easy to determine if IC's are being met | Ic's can be easily visualized from the car, so it is easy to determine if IC's are being met | Ic's can be easily visualized from the car, so it is easy to determine if IC's are being met | Knik TRP program contacted landowner about concern for capp at the site, we will continue to coordnate on this site. | Dec is requesting future sit visit with photos of backstop to ensure it is not being used for shooting. | IC compliance is being met. Peridoically revieweed every 5 years and last review was 2024 | Site has been compliant with IC's and perdiocially reviewed every 5 year. Last review was 2024 | Limited site access
ADEC Site link | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/24797 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/26123 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/23983 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/3327 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/25709 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/25757 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/26242 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/431
DATE ADDED TO INVENTORY | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IC | Advance approval required to transport soil or groundwater off-site. Groundwater Use Restrictions: No groundwater wells shall be installed on the contaminated area of the Site without prior DEC approval.Groundwater Use Restrictions New Construction Restrictions, Subdivision Restriction | Recorded Deed Notice- Notice of Environmental Contamination; Excavation and Soil movment restrictions; contaminated soil remediation should occur once accessible (when USTs are removed); groundwater monitoring ceased in 2018. | Groundwater use restrictions; New construction restrictions; Excavation / soil restrictions; Subdivision restriction; Movement or use of contaminated soil (including onsite) restricted. When contaminated soil is acessible, Remediation should occur | Capped : Maintenance / Inspection Of Engineering Controls & Advance approval required to transport soil or groundwater off-site. | Advance approval required to transport soil or groundwater off-site., Excavation / Soil Movement Restrictions | The newly constructed shooting range is to be managed in accordance with the September 2016 Environmental Stewardship Plan. Advance approval required to transport soil or groundwater off-site. Movement or use of contaminated material (including on site) in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70) | Periodic Review, Groundwater Use Restrictions, When Contaminated Soil is Accessible, Remediation Should Occur, Movement or use of contaminated material (including on site) in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70), Advance approval required to transport soil or groundwater off-site. | Excavation / Soil Movement Restrictions, The Army restricts entry by maintaining a locked gate at the entrance to OU-C, posting signs next to Eagle River for boaters, and regulating admission to OU-C through the Range Control. Five year review due in 2008.
NEXT IC REVIEW (PLANNED ACTION) | NONE | NONE | NONE | Reminder sent in Dec 2024; every 5 years. Next is 2029 | Reminder sent & Compliance met 10/29/2024: Next is 2029 | Reminder sent & Compliance met 6/14/2024: Next is 2029 | Reminder sent & Compliance met 10/15/2024: Next is 2029 | Last CERCLA ROD review was 2018, supposed to occur 2023 but see no record of ensuring IC compliance although it is recommended
IC STATUS | Cleanup Complete - Institutional Controls | Cleanup Complete - Institutional Controls | Cleanup Complete - Institutional Controls | Cleanup Complete - Institutional Controls | Cleanup Complete - Institutional Controls | Cleanup Complete - Institutional Controls | Cleanup Complete - Institutional Controls | Cleanup Complete - Institutional Controls
CLOSURE DATE | 2023-08-30 | 2024-03-07 | 2021-11-02 | 2012-10-23 | 2014-04-10 | 2017-12-06 | 2015-02-12
RP/PRP | Alaska Department of Corrections | Herman Schiesing, Service Oil & Gas, Inc. | Mr. Jay Daw. | ADOT & PF | ADNR-Clifford Larson | Tresspassers | ADOT & PF | US Department of the Army & Air Force
LANDOWNER | Guion Drew & Lisa | K & SC Corporation (Ms. Myong Kim) | Mr. Jay Daw. | ADOT & PF | ADNR-Clifford Larson | Kurt Steinert - MOA Public Works (LAW ENFORCEMENT) | ADOT & PF | US Department of the Army & Air Force
SITE TYPE | Petroleum | Lust | LUST | Lead? |  |  | Petroleum
COC's | BTEX, DRO, GRO, Benzene | DRO, GRO, Benzene, Napthalene, Phenanthene | DRO, GRO, RRO, Benzene,Toluene, | Lead | Every 5 years: Reminder sent and compliance met 10/29/2024. Next is 2029 | Lead, Benzo(a) pyrene | DRO, RRO | White Phosphorous, UXO
DATE of CONTAMINATION | 1995 | 1999 | 1990 - roughly | 1970-2000 public shooting range | Recognized in 2012 | recognized in 2011, contamination was yrs leading to then | Contructed in 1980, excavated in Oct 2013 | 1945 - 1980
ESTIMATED VOLUME | 10,000 & 5,000 gallon Gasoline and Diesel Tanks, 15 cubic yards of excavated to depth of 15 ft | 1545 released, Aprox 985 left unrecovered after initial clean-up | Originally had 2 4,000 gal UST's & a 2,000 gall diesel tank 2000- 2,600 cubic yards removed | N/A |  | 225 cubic yds of soil removed and disposed at landfill |  | UNKNOWN
MEDIA IMPACTED | Soil, Groundwater | Soil, Groundwater | Soil, Groundwater | Soil, Sediment - Freshwater | Soil | soil | soil | Soil, Sediment - Freshwater
POTENTIAL EXPOSURE PATHWAYS | Direct contact with surface soil, inhalation, outdoor air | Ingestion of contaminated soils and/or groundwater | Ingestion, inhalation, | migration to groundwater, Ingestion/Inhalation | Ingestion/ inhalation of impacted media | ingestion/ inhalation of contaminated media | Ingestion/ inhalation of impacted media | Ingestion of contaminated soils and/or groundwater
DWW w/I 1/4 mile? | Yes | N/A | Yes | YES | NO | Yes - | NO | NO
WELL-LINK | WELTS - Well Log 3221 | N/A | https://dec.alaska.gov/DWW/JSP/WaterSystemDetail.jsp?tinwsys_is_number=5376&tinwsys_st_code=AK&wsnumber=AK2218818%20%20%20%20%20%20 | https://gis.data.alaska.gov/datasets/SOA-DNR::dnr-well-log-welts/explore?location=61.599985%2C-149.126760%2C14.00 | N/A | WELTS link | N/A | N/A
POTENTIAL SUBSISTENCE IMPACTS | Yes | No | No | YES | NO | Yes - Peters Creek river? | NO
MONITORING WELLS (MW) | Yes | Yes | Yes | No | NO | No |  | Yes
MW STATUS | N/A | Decomissioned | MW3, MW7, & MW 8 remain as per landowners request for future sampling. MW13,MW14 & 15 were destroyed or are missing. 3 others were decomissioned | N/A | N/A | N/A
SITE MANAGER (SM) | Janice Wiegers | IC UNIT | IC Unit | IC Unit | IC Unit | IC Unit | IC Unit | IC Unit
CONTACT FOR SM | 907-451-2127 dec.icunit@alaska.gov | 907-465-5229 dec.icunit@alaska.gov | 907-465-5229 dec.icunit@alaska.gov | 907-465-5229 dec.icunit@alaska.gov | 907-465-5229 dec.icunit@alaska.gov | 907-465-5229 dec.icunit@alaska.gov | 907-465-5229 dec.icunit@alaska.gov | 907-465-5229 dec.icunit@alaska.gov
TRP History with Site | Yes: Review Closure Decision- completed 9.1.23; N/A: Review Closure decision, 9.1.2023; Yes: Review Closure decision, 6.27.22; NO: 2022-SV
LAST TRP ACTION | Check IC status - up to date | Reviewed closure letter and Institutional controls. No new database updates | Reviewed closure documents, IC's & confirmed IC compliance | Reviewed Closure documents, Reminder letter, and confirmed IC compliance | Reviewed Closure documents, Reminder letter, and confirmed IC compliance | Reviewed Closure documents, Reminder letter, and confirmed IC compliance | Reviewed Closure documents, Reminder letter, and confirmed IC compliance | Reviewed Closure documents, Reminder letter, and confirmed IC compliance
DATE OF LAST ACTION | 2025-04-01 | 2025-09-19 | 2025-04-01 | 2025-04-01 | 2025-04-01 | 2025-04-02 | 2025-04-01 | 2025-04-01
SITE VISIT BENEFICIAL (Y/N) | Yes | Yes | Yes | NO | Yes | NO | No | No
Reason for Site Visit | To show that there is no new construction on the site | To show there is no new exposed soil, or new constuction on the site | To show there is no new exposed soil, or new constuction on the site | Kyle recently performed SV and is engaged on the site | Yes, DEC would like photos of Backstop to ensure that it is not being used for shooting | Not priority | Not Priority | Limited Site access
LAST ADEC DATABASE ENTRY | IC compliance review completed on this date. An IC reminder letter was issued to the landowner. The next review will be in five years’ time. | Received signed and recorded copy of Environmental Covenant back from recorder's office and sent out final closure letter | Institutional Controls established and entered into the database. | Contacted by the ADF&G refuge manager to let DEC know that some minor repair of geotextile barrier will occur this week. The gravel and soil will be excavated down 1-2 inches as basic maintenance of the gravel cap. I provided approval for this work and the site diagram with locations is in the site file | DNR staff (SAIL) visited this site and provided photos to us of the cap and backstop. Based on the size of the trees, it doesn’t look like the backstop is used for shooting anymore. For future IC compliance reviews, we will request current photos to make sure that the property continues not being used for shooting. | IC compliance review completed on this date. An IC reminder letter was issued to the landowner. The next review will be in five years’ time. | IC compliance review completed on this date. An IC reminder letter was e-mailed to the landowner. The next review will be in five years’ time. | DEC reviewed and approved Draft 2021 Long-Term Management Report for XU022- Eagle River Flats. The report documented that dabbling duck mortality for white phosphorous was less than 1% in 2021, which has been the trend since 2006. In addition, the report sampled areas on and around the capped ponds for white phosphorous. White phosphorous was detected in only one sediment sample at a concentration of 0.0064 ug/g, which is below the project value of 0.01 ug/g. The LUCs and site restrictions remain in place and appear to be preventing unauthorized use of the area.
DATE OF LAST ENTRY | 2024-08-30 | 2024-03-07 | 2021-11-02 | 2025-06-02 | 2024-10-29 | 2024-06-14 | 2024-10-15 | 2022-04-14
LATITUDE | 61.4047 | -149.4685 | 61.3672 | 61.4875 | 61.5102 | 61.4174 | 61.4217 | 61.3097
LONGITUDE | 61.4081 | -149.4518 | -149.5137 | -149.2522 | -149.5608 | -149.5149 | -149.497 | -149.7078
ACREAGE | N/A | N/A |  | at least a 70 acre parcel |  | UNKNOWN |  | 6,000?
ADDRESS | 22189 South Birchwood Loop Road, Chugiak, AK 99567 | 20808 Bill Stephens Drive, Chugiak, AK 99567 | Mi. 18 Old Glenn Hwy.; , 16206 OLD GLENN HWY, Chugiak, AK 99567 | Mile 30.2 Glenn Highway, Rock Pit on Hwy West-Side, Palmer, AK 99645 | Access Road East of Hayfield Road at Lucy lake Drive, Wasilla, AK 99654 | Birchwood Street; NW of Birchwood Airport, Chugiak | 20651 Birchwood Spur Road; Birchwood Airport, Chugiak, AK 99567 | Eagle River Flats FTRS-22, Formerly Fort Richardson before 10/01/2010, Fort Richardson (JBER), AK 99505
BOROUGH | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska - susitna | Matanuska-Susitna | Matanuska-Susitna
CONSIDERED FOR DBAC | Likely not Eligible: There is a RP and controls are in place to limit environmental impact | Likely not Eligible: There is a RP and controls are in place to limit environmental impact | Likely not Eligible: There is a RP and controls are in place to limit environmental impact | Likely not Eligible: There is a RP and controls are in place to limit environmental impact | Likely not Eligible: There is a RP and controls are in place to limit environmental impact | Likely not Eligible: There is a RP and controls are in place to limit environmental impact | Likely not Eligible: There is a RP and controls are in place to limit environmental impact | Likely not Eligible: There is a RP and controls are in place to limit environmental impact
OVERLAP w/ KNIK? | NO | NO | NO | NO | YES | NO | NO | NO
OVERLAP w/ CVTC? | ? | ? | ? | NO | YES

## Sites Not on ADEC
SITE NAME | Mink Creek | Hilltop Recycling | Loretta French Sports Complex Dump | Matanuska River Dump | Dump at the Old Dykes by Matanuska River | Old Railroad Dump Near NVE | Dump Below 3 Bears on N. Birchwood Loop Rd. | Two Dumps in Woods SE of Ikluat Conservation Easement Picnic Grounds and near the Wildflower Wetlands | Lands around the Far End of Eklutna Lake | Birchwood Airport | Eklutna River Dump | Lazy Mountain Barrel Dump | Moose Creek RR Pilings | Chugiak Golden Wheel Amusements
ADDRESS | 16515 CENTERFIELD DRIVE #100 | 16849 Old Glenn Hwy | 18100 Old Glenn Hwy | 1/4 to 1/2 mile north of Eagle Ave. | N/A | Across RR tracks from Eklutna Village | N. Birchwood Loop Rd. |  |  |  | Eklutna River Canyon, Above Old Dam site | Uphill of access road to TH; can see from road | Mouth of Moose Creek | 18631 Old Glenn Highway
CITY | Eagle River | Chugiak | Chugiak | Palmer | Palmer | Chugiak | Chugiak | Chugiak | Chugiak | Chugiak | Chugiak | Palmer | Palmer | Chugiak
ZIPCODE | 99577-7719 | 99567 | 99567 | 99645 | 99645 | 99567 | 99567 | 99567 | 99567 | 99567 | 99567 | 99645 | 99645 | 99567
LATITUDE | 61.3961 | 61.3721 | 61.3952 | 61.6172 | unknown | 61.4629 | unknown | 61.4646 | 61.3414 | 61.418 | unknown | unknown | unknown | 61.3889
LONGITUDE | -149.48717 | -149.50492 | -149.4782 | -149.1062 | unknown | -149.3646 | unknown | -149.3527 | -148.9959 | -149.5074 | unknown | unknown | unknown | -149.4785
ACREAGE | 68.14 | unknown | unknown | unknown | unknown | unknown | unknown | unknown | unknown | unknown | unknown | unknown | unknown | unknown
LANDOWNER | EI | GARDNER ENTERPRISES LLC | N?A
PRIORITY | Priority | Priority | Priority | Priority | Priority | Priority | Priority | Priority | Priority | Priority | Priority | Priority | Priority | Not Priority
REASON | Site assesment will be completed soon with more information about contamination, currently owned by EI to be developed | Site is listed as a concern for NVE | Site is listed as a concern for NVE | Site is listed as a concern for NVE | Site is listed as a concern for NVE | Site is listed as a concern for NVE | Site is listed as a concern for NVE | Site is listed as a concern for NVE | Site is listed as a concern for NVE | Site is listed as a concern for NVE | Site is listed as a concern for NVE | Site is listed as a concern for NVE | Site is listed as a concern for NVE | Site is listed as a concern for NVE
TYPE OF SITE / COC's | possible leaching from landfill near Lorretta French Complex | junkyard- petroleum, hazardous chemicals | former landfill | dump, possible petroleum, hazardous chemicals | dump | possible hazardous chemicals | possible car dump | possible appliance, empty drum dump | lead, other possible contamination | possible future PFAS | vehicle, appliance, general dumping activities | 10-15 barrels, other debris | 30-50 creosote pilings | possible petroleum
TRP ACTION | Received email from Office of Grant Development. Site assesment will be conducted | Input in inventory | input in inventory | Site visit | Input in inventory | Input in inventory | Input in inventory | Attempted to locate - Unsucessful | Input in inventory | Input in inventory | Input in inventory | Site visit | Site visit & Coodinated with Kyle who is engaged on the site. | Contacted ADEC
DATE OF ACTION | 2025-09-19 | N/A | N/A | 2022 | N/A | N/A | N/A | 2022 | N/A | N/A | N/A | 2022 | 8.1.2025 | 2022
PROPOSED ACTIONS | Keep monitoring the site and request any data gathered during assesment to review | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Look into funding opportunities for cleanup; continue to document |  | Kyle from Knik is actively working on communicating with landowners (Railroad) to get site recognized and cleaned-up. We found that some of the Cresosote treated boards and pillings are partially submerged in the River which is habitat for all 5 salmon species.
SWS LINK | https://adec.maps.arcgis.com/apps/webappviewer/index.html?id=43a9fdcd23a04b54aad1e753327ffd53
ELIGIBLE for DBAC? | Yes, Coordinator will investogate for site eligibilty for DBAC. | Should review site and determine eligibility | Should review site and determine eligibility | Should review site and determine eligibility | Should review site and determine eligibility | Should review site and determine eligibility | Should review site and determine eligibility | Should review site and determine eligibility | Should review site and determine eligibility | Should review site and determine eligibility | Should review site and determine eligibility | Should review site and determine eligibility | Should review site and determine eligibility | Should review site and determine eligibility
ELIGIBLE for ANCSA | Possiblly, owned by EI & unknown date of contamination | [8 empty] | NO

## New Sites
SITE NAME | Sunset Auto Body Class V Injection Well | Eagle River, Speedway #5303 | Chevron #1252 | ADOC Hiland Mountain Correctional Center Former Shooting Range | AFSC Former Cross-town Pipeline, 1900 C Street Release | AFSC Former Cross-town Pipeline, 1600 C Street Release | Gay Subdivision Tract A3
SITE CONSIDERED FOR CLOSURE | Yes | decomissioning well, so close | Close to closure | NO | NO | NO | NO
HAZARD ID | 26906 | 27609 | 23705 | 25438 | 419 | 593 | 27241
PROBLEM | Under compliace under from EPA for well closure. Two shop drains flow into culvet pit and directly to a perforated drain pit outside the building. | Diesel UST tank cracked and leaked 10 gallons of diesel | After removal of 3, 10,000 UST's contamination was found exceeding groundwater migration levels | Used as a shooting range by Alaska Department of Corrections. Lead contamination in the soil exceed RDRA standard | Pressurized pipeline containing Jet A reported flowing into Chester Creek | Leak in fuel pipeline for Jet A. | Soil contamination found in planned parking lot area for Childcare facility.
PRIORITY | Prioritzed | Prioritized | Prioritized | Prioritized | Priotitized | Prioritized | Prioritzed
REASON | EPA is awaiting response from DEC and asked if a conditional closure letter is needed | Workplan for well decomission was requested in 2024, no other database entries since. Could be close to closure | DEC approved workplan for W. Cuumulative risk standards have been met. Could be close to closure, should continue to monitor site. | DOC is awaiting response from EPA, as of 5/2024 for approval to develop range abatement plan with Shannon & Wilson. No update since. | Biennial Grounwater monitoring is expected for compliancy, last report was 2023. Expected in 2025 | Biennial Grounwater monitoring is expected for compliancy, last report was 2023. Expected in 2025 | approved Vapor Intrusion assesment Workplan to asses potenital vapor intrusion at Head start building from nearby contaminated soil. Monitor database to see result of work completed.
ADEC LINK | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/26906 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/27609 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/23705 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/25438 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/419 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/593 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/27241
DATE ADDED TO INVENTORY | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07
STATUS | Active | Active | Active | Active | Active | Active | Active
RP / PRP | Sunset Auto Body | Speedway | CHEVRON PRODUCTS COMPANY | Alaska Department of Corrections | AFSC | AFSC | Jamie Grant and Jessica Hall
LANDOWNER | Sunset Auto Body | Speedway | CHEVRON PRODUCTS COMPANY | Alaska Department of Corrections | AFSC | AFSC | Cook Inlet Native Head Start
SITE TYPE |  | petroleum | Petroleum | Lead | Petroleum | petroleum | petroleum
COC'S | Napthalene, Chromium, tetrachloroethylene | GRO, DRO | Benzene, ethylbenzene, DRO, GRO. | Lead | GRO, DRO, | GRO, DRO, benzene | arsenic, DRO, GRO, napthalene
DATE OF CONTAMINATION | Well in use since 1988, contamination encountered 2018 | Discovered during routine check June 2021 | 1995 | 1980-1998 | 1988-1999 | 1989 | 2019
MEDIA IMPACTED | Soil, Groundwater? | soil, groudwater | Soil, Groundwater | Soil | Soil, Groundwater | Soil, Groundwater | Airspace in building, soil
ESTIMATED VOLUME | Unknown | 10 Gallons of Diesel | N/A | N/A | N/A | N/A | N/A
POTENTIAL EXPOSURE PATHWAYS | Ingestion of soil | ingestion of Soil or Groundwater | Ingestion of soil or groundwater | Ingestion/contact with soil | Ingestion of soil or groundwater | Ingestion/contact with soil or groudwater | Ingestion/contact with soil. Airspace
DWW WITHIN 1/4 MILE | Yes 77ft away | Yes | Yes | No | No | No | No
WELL LINK | Onsite, but not listed on WEB | https://dec.alaska.gov/DWW/JSP/WaterSystemDetail.jsp?tinwsys_is_number=1854&tinwsys_st_code=AK&wsnumber=AK2215524%20%20%20%20%20%20 | https://dec.alaska.gov/DWW/JSP/WaterSystemDetail.jsp?tinwsys_is_number=1854&tinwsys_st_code=AK&wsnumber=AK2215524%20%20%20%20%20%20 | N/A | N/A | N/A | N/A
POTENTIAL SUBSISTENCE IMPACTS? | NO | ?? | No? | Yes | Yes | Yes | Yes
MONITORING WELLS | NO | Yes | Yes | No | Yes | Yes | No
STATUS OF MW | N/A | Workplan requested to decomission | Active | N/A | Active | Active | N/A
SITE MANAGER | Janice Wiegers | Kris Dent | Rebekah Reams | Michael Hooper | Shawn Tisdell | Shawn Tisdell | Dawn Wilburn
SM CONTACT | 907-451-2127, janice.wiegers@alaska.gov | 907-726-3411, Kris.dent@alaska.gov | 907-451-2144, rebekah.reams@alaska.gov | 907-451-5174, michael.hooper@alaska.gov | 907-451-2752, shawn.tisdell@alaska.gov | 907-451-2752, shawn.tisdell@alaska.gov | 907-262-8200
LAST TRP ACTION | Contacted Site Manager | Input in inventory and reviewed databse info | Reviewed database and determined ANCSA, DBAC, Closure eligibility | Input in inventory and reviewed database information | Site Visit | Site Visit | Reviewed site
DATE OF ACTION | 8.7.25 | 8.7.25 | 2025-09-19 | 8.7.25 | 9.30.25 | 9.30.25 | 8.7.25
PROPOSED NEXT ACTION | Contant SM and determine if site is eligible for conditional closure or if there are any remaining needs to be met | Contact site manager for update of closing status | Contact site manager for update of closing status | Contact SM to determine if approval to develop range abatement will go through | Contact site manager to determine when groundwater monitoring will occur for 2023, last monitorin event was 2023 and supposed to be Biennial | Contact site manager to determine status of moving forward with site characterization | Contact site manager to determin when Vapor intrusion assesment will ocurr and get update on site.
SITE VISIT Y/N | NO |  |  |  | YES | YES | NO
REASON | Site is close to closure |  |  |  | Coordinator |  | Access
LAST ADEC DATABASE ENTRY | Received email from EPA (Donna Ortiz). EPA waiting for response from us - although if needed could send a conditional closure letter that says injection well is closed but work with DEC on contamination. | Groundwater monitoring well decommissioning workplan requested | DEC approved the Work Plan for Decommissioning of Eight (8) Groundwater Monitoring Wells which proposes to decommission existing groundwater monitoring wells MW-1R, MW-2, MW-3, MW-4, MW-5, MW-6, MW-8 and MW-9 in September 2025. | DOC notified EPA that they are waiting final approval for funding to develop a plan for range abatement. DOC plans to work with Shannon & Wilson. The DOC point of contact will be the HMCC Facility Manager, John Gard. | One five gallon container of jet fuel contaminated soil from site characterization activities at both the 16th Avenue & C Street (Haz ID 593) and 19th Avenue and C Street (this site) was transported and disposed at US Ecology Viking Facility in Anchorage. | teleconference held with Menzies Aviation and their new consultant from SLR to discuss the site history and path forward for additional site characterization of pipeline related contamination to the southwest, in the direction of the Cook Inlet Native HeadStart. Menzies plans to conduct additional soil and groundwater delineation of petroleum contamination toward the HeadStart building and will be preparing a workplan for this effort. | Approved the revised Vapor Intrusion Assessment Work Plan dated February 18, 2025. Two rounds of indoor air and near-slab soil gas sampling are proposed to assess potential vapor intrusion at the Head Start building from nearby contaminated soil. Prior to sampling a building survey will be performed. During each sampling event, six primary indoor air samples and a duplicate will be collected as well as three near-slab soil gas samples
DATE OF LAST ENTRY | 2024-11-26 | 10.7.24 | 2025-09-03 | 2025-05-20 | 2025-04-11 | 2025-08-30 | 2025-03-11
ACREAGE | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ADDRESS | 21442 N Birchwood Loop Road, Chugiak, AK 99567 | 12139 Old Glenn Highway, Eagle River, AK 99577 | 11836 Old Glenn Hwy., Eagle River, AK 99577 | 9101 Hesterberg Road, Eagle River, AK 99577 | 1900 C Street, W of C & S of Chester Cr., Anchorage, AK 99501 | 1600 C Street, W of C & N of Chester Cr., Anchorage, AK 99503 | 370 West 16th Avenue, Anchorage, AK 99501
BOROUGH | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna | Matanuska-Susitna
LATITUDE | 61.4078 | 61.3296 | 61.3276 | 61.3023 | 61.2034 | 61.2053 | 61.2052
LONGITUDE | -149.483 | -149.5672 | -149.5707 | -149.575 | -149.8878 | -149.8876 | -149.8881
ELIGIBLE For DBAC | NO there is a RP | NO there is a RP | NO there is a RP | NO there is a RP | NO there is a RP | NO there is a RP | NO there is a RP
ANCSA LANDS | NO | NO | NO | NO | NO | NO | NO
CONSIDERED FOR CLOSURE | Yes, shop drain was capped and site is compliant with regulation. EPA is awaiting response from DEC asking if conditional closure letter is needed, 2024 | No, but it is close. All results in 2022 below clean:up levels and there is a request to decomission well | No, but it is close. All results in 2022. Cuumulative risk standards have been met and 8 MW approved to be decomissioned | NO | NO | NO | NO
OVERLAP W/ CVTC? | no | ? | ? | ? | ? | ? | no
OVERLAP W/ KNIK? | ? | ? | ? | ? | ? | ? | ?