## Definitions and Info
ADEC Site Status:
Active: | A location where confirmed contamination is present at levels above state action levels and requires further action.
Closed: | A location that has reached one of two official regulatory statuses under the Contaminated Sites Program: "Cleanup Complete"
Closed with IC's: | A contaminated site where residual contamination remains above standard cleanup levels, but human and environmental exposure is controlled through the use of Institutional Controls (ICs)
IC's: | Insitutional Controls (IC) are administrative and legal measures designed to minimize the potential for human exposure to the remaining contamination and protect the integrity of the cleanup efforts. These are non-engineered controls, unlike physical barriers like a clay cap
Abbreviations:
SM: | Site Manager
SMC: | Site Manager Contact (NVE contacted via email or call the site manager)
SV: | Site Visit
RP: | Responsible Party (for contamination)
ABCA: | Analysis of Brownfield Clean-up Alternative Methods
DBAC: | DEC Brownfields assesment and clean-up (grant funding source)
LUST: | Leaking Underground Storage Tank (UST)
NALEMP: | Native American Lands Environmental Mitigation Program
MOA: | Municipality of Anchorage
FUDS: | Formally Used Defense Sites
USACE: | U.S Army Corps of Engineers
EPA: | Environmental Protection Agency
ADEC: | Alaska Department of Environmental Conservation
ADNR | Alaska Department of Natural Resources
ADFG | Alaska Department of Fish and Game

## New Sites Added to Inventory
SITE | Sunset Auto Body Class V Injection Well | Eagle River, Speedway #5303 | Chevron #1252 | ADOC Hiland Mountain Correctional Center Former Shooting Range | AFSC Former Cross-town Pipeline, 1900 C Street Release | AFSC Former Cross-town Pipeline, 1600 C Street Release | Gay Subdivision Tract A3 | 3901 Hayes Street
BACKGROUND | Under compliace under from EPA for well closure. Two shop drains flow into culvet pit and directly to a perforated drain pit outside the building. | Diesel UST tank cracked and leaked 10 gallons of diesel | After removal of 3, 10,000 UST's contamination was found exceeding groundwater migration levels | Used as a shooting range by Alaska Department of Corrections. Lead contamination in the soil exceed RDRA standard | Pressurized pipeline containing Jet A was reported flowing into Chester Creek | Leak in fuel pipeline for Jet A. | Soil contamination found in planned parking lot area for Childcare facility. | The Phase 1 assesment conducted found several recognized environmnetal conditions, including being a staging area for contruction 1982-2012; evidence of illegal dumping; nearby Tesoro (olsen Gas Service Site; Nearby Former Auto Repair shop; and there is presence of a ceek on site that was channelized.
STATUS (Active/Closed) | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE
SITE ADDRESS | 21442 N Birchwood Loop Road, Chugiak, AK 99567 | 12139 Old Glenn Highway, Eagle River, AK 99577 | 11836 Old Glenn Hwy., Eagle River, AK 99577 | 9101 Hesterberg Road, Eagle River, AK 99577 | 1900 C Street, W of C & S of Chester Cr., Anchorage, AK 99501 | 1600 C Street, W of C & N of Chester Cr., Anchorage, AK 99503 | 370 West 16th Avenue, Anchorage, AK 99501 | 3901 Hayes Street, Anchorage, AK 99503
LATITUDE, LONGITUDE | 61.407838,-149.482951 | 61.3296, -149.567200 | 61.327556,-149.570702 | 61.3023 , -149.574950 | 61.203417, -149.887767 | 61.205298, -149.887614 | 61.205156, -149.888120 | 61.185622, -149.908467
LANDOWNER | Sunset Auto Body | Speedway | CHEVRON PRODUCTS COMPANY | Alaska Department of Corrections | AFSC | AFSC | Cook Inlet Native Head Start | Cook Inlet Housing Authority
RP | Sunset Auto Body | Speedway | CHEVRON PRODUCTS COMPANY | Alaska Department of Corrections | AFSC (menzies aviation) | AFSC (menzies aviation) | Jamie Grant and Jessica Hall, Menzies Aviation
ACREAGE / SIZE | Site ~1.09 acres | 1.56 acres | ~1 acre | 2.5 acres | ~2 of contamination (503 acre parcel) | 1.77 | 3.8 | 3.68
TYPE of SITE (contamination) | Petroleum: Mechanic Shop Floor drains | Petroleum: LUST | Petroleum: LUST | Hazardous Substances: Lead | Petroleum: Pipeline Release | Petroleum: Pipeline Release | Petroleum (associated with AFSC former cross town pipeline release | Hazardous substances: petroleum, Aresenic, Lead,
ADEC LINK | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/26906 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/27609 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/23705 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/25438 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/419 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/593 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/27241 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/27034
SITE WORK | Theta Environmental worked with EPA in 2018 to plan work on site which was conducted in 2019. This included sealing the injection well with concrete, cutting the floor inside the shop to expose the pit, removing and super sacking contaminated soil from the pit. Most recent water sample found no concentrations of contaminants. EPA is currently waiting from a response from ADEC about site closure and potentially needing a contitional closure letter. | In 2021 Soil was transported offsite to be treated or disposed of as well as three 55 gal Drums of Diesel. A Release investigation was performed by Stantec. New soil borings and groundwater monitoring well were installed in 2022. All sample results for contamination were below ADEC clean-up levels. (ADEC will evaluate the site for closure) 10/2024 a grounwater well decomissioning workplan was requested. | Site has had Long Term Monitoring performed by Chevron Environmental Management Company, (Arcadis) since 2023. 9/25 ADEC approved to decomission 8 groundwater monitoring wells because samples have been below the ADEC GCLs since March 2023, with the exception of lead during the most sample. Site closure request was sent march 21st, 2024. Waiting for ADEC to review this request and evaluate the site. | In 2018 Shannon and Wilson(SW) performed a site characterization. Workplan for Clean-up activities was received 2/2019. 2023 Alaska Department of Corrections contact ADEC about potential funding for site work. 5/24 DEC notified EPA they are waiting on final approval for funding to develop a plan for range abatement work with SW. | Clean-up work at this site began in 1989 and continued with recovery wells. In 1990 75.6 gallons of Jet A fuel were recovered. In 2006 monitoring wells were installed on the site. In 2008 two of the recovery wells were capped. Annual grounwater monitoring continued for until 2017 when Ahtna environmental stepped in to characterize the extent of contamination which included installing more grounwater monitoring wells. 2019 sampling showed a decreasing trend in contamination levels but Ahtna reccommended to continue with Biennial sampling until below clean-up levels. Additional site characterization continued in 2024 and a 5 gal container of Jet Fuel was removed and disposed of. | This site is associated with 1900 C street and has had a similar history. In 2024 the Biennial sampling report showed that contamination extends hurther west (towards cook inlet headstart) than previously delineated. 8/24 DEC met with Menzies aviation and new consultant from SLR to discuss the plan for additional site characterization. | Site was identified in 2020. In 2021 a ltter from Cook Inlet's legal representative suggested that Menzies aviation was the source of contamination. This site is associated with AFSC Former Cross Town Pipeline, 1600 and 1900 C street release sites. In 2023 ADEC sent RP a request for workplan to de submitted for futher site characterization. 11/2024 a Vapor Intrusion Assesment workplan was submitted, and it was approved 3/25. | Site was assessed using MOA's EPA Area-wide assessment grant. Found presence of contaminates in subsurface soil and groundwater above migration to groundwater levels, ADEC sent RP request for workplan, but no response until 2022, when RP moved back from out of state. Sampling and Analysis was approved and completed 2023. 3/24 test pits wer advanced in areas with documented contamination from previous assesment. 5/24 ADEC approved a sampling and analysis workplan from Nortech that includes additional soil borings and monitoring wells. 10/25 Sampling and Anlyiss plan submitted by MOA to conduct addtional site characterization under Brownfield Coalition Assessment Grant.
NVE's HISTORY w/ SITE | NA | NA | NA | NA | NA | NA | NA | NA
NVE's ACTIONS WITH SITE (COORDINATOR) | Coordinator contacted Site Manager Requesting update about status of the site and if there will be additional needs for closure | Coordinator added site to Inventory and reviewed database information | Reviewed database and determined ANCSA, DBAC, Closure eligibility | Added site to Inventory and reviewed database information | Site Visit | Site Visit | Added site to Inventory and reviewed database information & Vapor intusion workplan | Added site to Inventory and reviewed database information
DATE OF ACTION | 2025-08-07 | 2025-08-07 | 2025-09-19 | 2025-08-07 | 9.30.25 | 9.30.25 | 2025-08-07 | 2025-08-07
NEXT ACTION | Coordinator will keep monitoring site/database for additional updates about closure or additional requirements after their internal review of site. | Site may be close to closure b/c ADEC requested workplan for decomissioning monitoring well. Coordinator will Keep reviewing database and potentially reach out to SM | Coordinator will contact site manager for update of closing status and if ADEC has reviewed site closure request | Coordinator will Contact SM to determine if funding came through and if work will continue to develop range abatement | Coordinator will Contact site manager to determine when groundwater monitoring will occur for 2023, last monitorin event was 2023 and supposed to be Biennial | Coordinator Contact site manager to determine status of moving forward with site characterization | Coordiantor will contact SM to determine when Vapor intusion assesment, building survey, and sampling will be done. | Workplan for sampling and anlysis was approved by ADEC 10/20/25. Coordinator will monitor this site and review reports that come from the sampling.
Is Site ready for unrestricted use after previous acctions. (or will there be IC) | NO, likely to be closed with IC | NO, there was still contamination in soil, so if it is closed there will likely be an IC | NO, still residual contamination. Closure will likely require an IC | NO, still active site with contamination | NO, still active site with contamination | NO, still active site with contamination | NO, still active site with contamination | NO, still active site with contamination
Type of IC | Drain was capped and sealed, no longer available for use and vehicles must we washed at a different location | NA | NA | NA | NA | NA | NA | NA

## Sites with Ongoing Work & Needs
SITE | Eklutna Army Site | Old Matanuska Townsite | Eklutna Tailrace | ADFG Goose Bay Former Boat Launch | Briggs Property | Former Peter's Creek Texaco | ADNR Goose Bay State Game Refuge Creek Dump | Matanuska Maid Block | AmeriGas Petrolane | ADOT & PF Palmer Maintenance Facility
BACKGROUND | Old US Armysite used for supply and storage. Had a number of buildings, storage lots, heli landing pad. Site also has AST's. drum piles. Transformers, dump sites, and potential UST | Owner stockpiled numerous hazardous materials/wastes onsite, leading to soil contamination. EPA removal action recently took place. | Man-made channel with misc. solid waste including cars, Fridges, Steel drums, and dumped alongside. | Trespass shooting range, dump- lead, possible petroleum | City of Palmer unpermitted dump-site run-off contaminating Briggs property | Former gas station with petroleum contamination. 197.7 tons of soil excavated with no groundwater investigation to date. Current site use unkown | military dump, including abestos materials. Landfill with 20-30 transformers allegedly buried. 55 gallon drums with soil staining | Full extent of soil contamination has not been defined. Chromium and arsenic found to be naturally ocurring, but other contaminants are present from past or current use | Leaking in piping between UST and fuel dispenser. Stockpiles on site 4 12,000 gallon UST's as well as their piping removed in 1994. | multuple UST's removed and levels of DRO and lead remain at limits of excavation. 45 cubic yds of soil stockpiled on site, but not located on site visit in 2009.
STATUS (Active/Closed) | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | ACTIVE
SITE ADDRESS | Eklutna Village Road, Chugiak, AK 99567 | East D Street and, South 2nd Street, Palmer, AK 99645 | 13145 S. Old Glenn Highway, Palmer, AK 99645 | Cameo Drive; NW of W End of Goose Bay Airstrip, ~10 Miles SSW of Big Lake, Big Lake, AK 99652 | ~Mile 17 Old Glenn Hwy., Palmer, AK 99645 | 20943 Bill Stephens Drive, Chugiak AK 99567 | Goose Bay NIKE Site Access Road - Cameo Drive, Near the end of Goose Bay Knik Road, Big Lake, AK 99652 | 325 E Dahlia Avenue, Palmer, AK 99645 | 6951 East Blue Lupine Drive, Mile 36.5 Parks Highway, Palmer, AK 99645 | 289 Springer Loop Rd., Palmer, AK 99645
LATITUDE, LONGITUDE | 61.458812, -149.380739 | 61.541272, -149.227428 | 61.47708, -149.16178 | 61.392275, -149.847047 | 61.604296, -149.083182 | 61.409183, -149.446614 | 61.39796, -149.86689 | 61.600542, -149.109638 | 61.563676, -149.275264 | 61.563676, -149.275264
LANDOWNER | NVE | multiple properties (Block 4 Lots 1, 2, 3, 4, 5, 12, 13, 14, 15; Block 2 Lots 5-15) with multiple owners | ADNR/managed by ADF&G | ADF&G | Ray Briggs | David-McCabe, Dawn Water Co. | ADNR | 7 Parcels of land w/ various owners | Petrolane Gas Service. | ADOT
RP | DOD, United States Army | Gerald & Wanda Poirier, Estate of Gerald Poirier | City of Palmer? | ADF&G | City of Palmer | David-McCabe, Dawn Water Co. | ADNR | 7 Parcels of land w/ various RP'S | Petrolane Gas Service. | ADOT
ACREAGE | ~ 32 Acres | ~0.23 acres | 2.81 | ~1 | ~7.2 | 0.45 acres | ~2.3 | 8.74 | <0.5 acre | ~13
TYPE OF SITE (contamination) | Petroleum | Petroleum & Hazardous Substances: glycol, lead, solvents, asbestos-containing materials, more | Hazardous Site & Petroleum | Hazardous substances: Lead | Hazardous Substances | Petroleum: LUST | Hazardous Substaaces: Abestos, illegal shooting range- lead, possible petroleum, possible hazardous chemicals, dump. | Hazardous Substances: lead, mercury, benzo(a)pyrene, pesticides, Napthalane, GRO, DRO, RRO | Petroleum: LUST | Petroleum: LUST
ADEC LINK | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/25642 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/4004 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/27750 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/26136 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/2597 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/24881 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/4304 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/26608 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/22894 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/24742
TRP HISTORY | NVE has obtained funding through NALEMP to perform surveys and cleanup actions for this site. Since 2017, drums, contaminated soils, and various surface debris have been located and removed; 2023- NALEMP project for surface debris cleanup; 2024- submitted funding request for TCE pump and treat cleanup pilot project and solar farm redevelopment at this site (EPA Community Change Grant) SM contact 2025; Emailed FUDS site manager to request any new information or data from summer site work (no response) 9/25 | Targeted Brownfields Assessment, 2018; Stakeholder meeting 2020; 2023- Multiple meetings w/ EPA, DEC, Borough; EPA testing and removal action underway, surface debris largely removed. 2024- reviewed removal action report from EPA, discussed w/EPA coordinator. Attempted Site Visit, but cut short due to safety concerns (hostile person at site); SMC 2025; | DBAC application, 2022 (awarded); Phase 1 Investigation started; SV 2022; reviewed findings from Phase 1, partial Phase 2; submitted for additional funds to continue characterization work; 2024- joint site visit; review assessment reports. 2025 - SV & funding research; 10/15/25 SM Contact | SMC, 2021; SV 2021; SMC, SV w/ ADEC, ADNR, ADOT, and Chickaloon TRP May 2022; 2023- meetings held with DHHS regarding human exopsure risk to lead at site. Followup attempts have gone unanswered. | SMC- Jan. 2022; SMC Dec. 2022 (new site manager); SMC 2023 | SMC, 2018; SMC, 2021; SMC, 2024; SMC 2025: SV2025 | SMC, 2021; SV 2021; SV May 2022; 2024 sent to FUDS; | NA | SMC, 2021; SMC 2022; SMC 2023 | SMC, 2025
SITE WORK | Cleanup and investigation activities began in 2005 when the Native Village of Eklutna (NVE), under NALEMP cooperative agreements, removed military debris and buried drums. In 2008–2010, petroleum contamination discovered during gravel extraction prompted additional sampling and contaminated soil removal by NVE and site operators, with ADEC oversight. Since 2010, the U.S. Army Corps of Engineers (USACE) has managed the site under the FUDS/CERCLA process, conducting extensive soil, groundwater, and vapor investigations, with high-resolution site characterization and VOC-focused studies continuing through 2025. NVE signed a Cooperative agreement 9/25 for NALEMP to address lead contaminationin the soil in 2026 and 2027. | 2008 ADEC with the Mat-Su Borough performed a site inspection. Reccomended that Prevention and Emergency Response Program (PERP) follow up due to land being up gradient to the wetland. 2009 PERP contracted Emerald Alaska to address the contamination. Drums and other hazardous substances still remained on site. 2016 SV found and documented the remaining contamination. 2018 the remaining drums were overpacked and removed from the site. 9/18 NVE was awarded a Targeted brownfield Assesment grant. 4/23 ADEC met with NVE to discuss a Site Characterization by EPA that will occur10/23. Time-Critical Action Removal was performed at the site by EPA and addresses the remaining contamination and hazardous materials. ADEC is in review of this report and evaluating the site for any addtional needs before closure. | 8/2022 NVE worked with EI, ADF&G, & ADNR to get a DBAC grant awarded for a Phase I assessment. Shannan & Wilson (SW) visited the site with all parties prepare for the DBAC project. SW performed a site characterization. Additional site assessment report submitted 4/2024 Tailrace site was awarded an addtional DBAC grant to provide support for clean-up planning (developing ABCA) ABCA was approved 7/2025. ADEC met with NVE staff to discuss remainign contamination that is preventing closure. | 8/2016 boat launch area was capped with clean fill by ADFG. 10/2021 The lead contaminated area and barge landing site were also capped. 12/2021 NVE staff performed Site visit and provided report and map of the area depicting area used for the educational fish permit. Kyle Robillard from Knik was awarded addtional funding for site chracterization that will take place summer of 2026. | Gilfilian Engineering Phase II Environmental Site Assessment report 4/1996. Additional water sampling found PCE and Groundwater(GW) contamination at levels that clean-up is not warranted or required. ADEC reccommended a GW gradient investigation be performed. report from Gilfian indicated source or contamination does not originate from teh Briggs Property. in 11/2000 Property owner (Ray Briggs) testified in court regarding the ADEC's oversight and review of the site and levels of contamination. Site has been tied up in legal intricacies since the Property owner recntly passed away and the case was enver resolved. Transfer of property is complicated and may be purchased. | Site was created in 1991, assesment found containation. 2/1999 Partial release investigation conducted during the removal of 197.7 tons of contaminated soil. Soil contamination was left in-situ. ADEC requested a Release investigation workplan for the site 4/1999. The workplan was not provided. Multiple requests and letters were sent until a SV was performed in 2018. 2/2019 ADEC reviewed the site characterization workplan from BGES. Cost restricted site work in 2019. ADEC discussed potential funding sources for site work with RP's representative. 6/25 Workplan was approved for site characterization activities to determine vertical extent of contamination. | DOC applied to renew Solid Waste Disposal permit 5/1986. ADEC inspection found inadequate cover material and issued notice of violation. Listed as potentially hazardous 1987. 6/2002 Site investigation report prepared for Corps. 2006 Shannon and Wlison performed Surface Stain Characterization. 9/2009 through SPAR term contract brownfield funding awarded to Oasis. 6/2010 Oasis provided assesment and clean-up plan, conducted a SV, and activities found potential source areas. Due to limited Geospatial data the army corps of engineers Funds program is delayed in completing a Inventory Project Report(INPR). 10/25 provided INPR, ADEC had addtional comments and it is currently in review | 2014 mointoring wells were installed to sample groundwater. Wells were sampled in 2014 and 2015. Exceedances in migration to groundwater and residential human health clean-up levels. However there was a reduction in 2015. ADEC requested field notes from sampling event in 2015. No other substantial updates on database. | UST and soil was excavated ~1994. 1995 N-M contracted to assist in the remediation of contaminated soils stockpiled from UST removal. ADEC approved Soil Treatment and Cell plan submitted by Gilfilian Engineering and Environmental testing, Inc. in 1996 and a soil vapor extraction system in 1999. 11/2002 Long term Groundwater monitoring was established to happen quarterly. continued GW monitoring through 2014 when wells that were not exceeding contamination levels were decomissioned. Workplan request was issued by ADEC 2/2024 for additional GW monitoring wells, soil and vapor investigations, as well as monitor existing wells to delineate soild and GW after the last update was 2018. | 1998 ADEC received final report from UST removal. There is a soil stockpile onsite that resulted from this site work. 6/2009 ADEC and ADOT & PF met for a site visit. They could not locate the stockpile and located a AST in the area of the former UST's. 9/2015 a release was discovered from the AST in the same area as the active site. Some of the soil was excavated but not all contamination was removed because of time restrictions. Remaining DRO contamination at the site.
NVE's PREVIOUS ACTION (Coordinator) | Assist in developing and Review cooperative agreement to obtain NALEMP funding to address lead contamination. | Requested and Reviewed Time Critical Actiton Removal report and completed newsletter article with update | Meeting w/ SM to discuss most recent database entSite Characterization work under EPA | Met with Knik TRP Kyle to dicuss thriving communties grant that was awarded for work on this site. | Discussed site updates with TRP Coordinator Kyle from Knik. Reviewed reports he obtained. | Coordinator performed site visit. Noticed improperly contained and labeled Investigation Derived waste. Contacted SM and provided photos. SM contacted contractor to properly seal drums and use more permanent labeling in future. | Met with Knik TRP coordinator and discussed status of the site. Still awaiting the Project inventory report to become available soon. Kyle will send it with a site update once available. | Contacted SM to ask for status update and if there are any planned site activities for this site. | Reviewed site while developing inventory, prioritized site for future action. | Received email from SM after requesting an update and reviewed most recent ADEC SV report. Site requires additional characterization to determine needs.
DATE OF ACTION | 10/xx/2025 | 2025-08-04 | 2025-10-23 | 2025-11-15 | 2025-07-21 | 9.5.25 | 2025-11-15 | 2025-12-23 | 9.19.25 | 2025-09-23
NVE's NEXT ACTION | USACE conducting stage 2 in August. Expect update / report after that | Reach out after Fall; they will perform site closure review here soon to identify any remaining needs to close the site. | Coordinator will continue to review site and consider any future actions again before the next DBAC application period | Kyle will reach out during future meetings with Bill for Methodology, sampling plans, and workplan for the thiving community funding | Continue to discuss site at QTRLY meetings with Kyle and see if progress is made with landownership. | Anticipate report from investigation work that was done and potentially request/review document. | Check again in November/December for report to be made public. Discuss potentially in 2nd QTR meeting while reviewing shared inventories. | Contact SM and determine status of site and why is it stagnant/ what its needs are for progress | Contact Sm to see if Rp ever responded or should be contacted again to monitor existing wells, add additonal Groundwater monitoring wells & vapor investigiations FY25 | Keep site in mind for Phase I and Phase II site assesment's and capacity development research for ways to push this forward.
Is there an IC in place? | No | No | NO | NO | NO | NO | NO | No | No | No
Type of IC | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Is Site Suitable for Unrestricted use after Closure. | NO | Potentially, site was cleaned up. ADEC is evaluating this site to see if there are any additional needs or IC's to put in place before closure. | NO | NO | NO | NO | NO | NO | NO | NO

## Sites Closed with Requirements
SITE | ADNR Cottonwood Creek, former Shooting Range | ADOT Knik River Rest Stop, AKA Reflections Lake | Circle S Grocery Store | Peter's Creek Chevron | AAA Transmission Exchange, former Chugiak Texaco
BACKGROUND | Unauthorized (public) shooting activities leading to lead contamination in soil. | previously a shooting range which led to lead contamination in soil | Gasoline and Diesel tanks leaked and contaminated a DWW | Leak from around sumps for underground storage tanks. | Contamination from leaking (diesel) above and underground (Gasoline) storage tanks from previous gas station
STATUS (Active/Closed) | Closed with Instutional Controls | Closed with Instutional Controls | Closed with Instutional Controls | Closed with Instutional Controls | Closed with Instutional Controls
SITE ADDRESS | Access Road East of Hayfield Road at Lucy lake Drive, Wasilla, AK 99654 | Mile 30.2 Glenn Highway, Rock Pit on Hwy West-Side, Palmer, AK 99645 | 22189 South Birchwood Loop Road, Chugiak, AK 99567 | 20808 Bill Stephens Drive, Chugiak, AK 99567 | Mi. 18 Old Glenn Hwy.; , 16206 OLD GLENN HWY, Chugiak, AK 99567
LATITUDE, LONGITUDE | 61.510156, -149.56081 | 61.4875, -149.252222 | 61.404709, -149.468506 | 61.408098, -149.451832 | 61.367161, -149.513689
LANDOWNER | ADNR-Clifford Larson | ADOT & PF | Guion Drew & Lisa | K & SC Corporation (Ms. Myong Kim) | Mr. Jay Daw.
RP | ADNR-Clifford Larson | ADOT & PF | Alaska Department of Corrections | Herman Schiesing, Service Oil & Gas, Inc. | Mr. Jay Daw.
ACREAGE | 13.11acres | 75 | ~ 3 acres | ~2 acres | 3 acres
TYPE OF SITE (contamination) | Hazardous Substances: Lead | Hazardous Substances: Lead | LUST: Petroleum | LUST: Petroleum | LUST: Petroleum
ADEC LINK | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/25709 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/3327 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/24797 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/26123 | https://dec.alaska.gov/Applications/SPAR/PublicMVC/CSP/SiteReport/23983
SITE WORK | Clean up was completed at this site in 2014. IC controls were set in place and site no longer poses a unnacceptabe risk to human helath if it stays compliant. | 2004 the backstop areas were excavated, soil was super sacked, disposed of, and site was closed. Caps were put in place ( 1 foot thick). 3/2010 The site was characterized and reopned after delineating the extent of lead contamination. 5/2012 lead contaminated areas were capped wtih 6" gravel, geotech liner, and topsoil. The site was reclosed 10/2012 with IC's in place to be reviewed every 5 years. | Work at Circle S Grocery began in 1995 under ADEC’s LUST program with UST removal and soil excavation, followed by additional investigation in 1999. The remaining 15,000-gallon tank was removed in 2012 under ADEC oversight. A detailed release investigation was completed in 2014 by ERM (for the insurer), and ADEC required ongoing groundwater and drinking-water monitoring with monitoring wells installed in 2015. Continued monitoring and delineation by ERM and RSE led to replacement drinking water wells in 2022, and ADEC (Janice Wiegers) closed the site with IC's | Contamination was identified in September 2013 after an ADEC IPP inspection found out-of-compliance UST sumps. RP and contractor removed contaminated soil and began investigation under ADEC oversight. From 2014–2015, the RP’s consultant (BGES) completed soil borings, installed and sampled monitoring wells, and carried out a drinking-water well survey/sampling, while ADEC (Robert Weimer) directed additional delineation, groundwater monitoring, and vapor intrusion evaluation. ADEC approved pilot testing and then installation of a soil vapor extraction (SVE) remedy (installed/operating starting 2018), and after continued monitoring and review (including Michael Hooper), the SVE system and wells were decommissioned in June 2023 and the site was closed with IC's | Petroleum contamination from USTs and an AST was identified in 1992, followed by site characterization and installation of monitoring wells under ADEC oversight. Corrective actions in 2002–2004 included excavation and thermal treatment of contaminated soil and installation/operation of a soil vapor extraction (SVE) system, and the on-property Class A drinking water well was sampled and found non-detect. After additional characterization and monitoring by environmental consultants and regulatory oversight, the site was closed with IC's
NVE's TRP HISTORY | 2022-SV | Knik TRP performed SV and noticed IC fell out of compliance. 6/2/25 cap was repaired. | Review Closure Decision- completed 9.1.23 | Review Closure decision, 9.1.2023 | Review Closure decision, 6.27.22
NVE's PREVIOUS ACTION (Coordinator) | Reviewed Closure documents, Reminder letter, and confirmed IC compliance | Reviewed closure requirements, reminder, and discussed with Kyle | Check IC status - up to date | Reviewed closure letter and Institutional controls. No new database updates | Reviewed closure documents, IC's & confirmed IC compliance
DATE OF ACTION | 2025-04-01 | 2025-04-01 | 2025-04-01 | 2025-09-19 | 2025-04-01
NVE's NEXT ACTION | SV: Dec is requesting future sit visit with photos of backstop to ensure it is not being used for shooting. | Periodically review | potential site visit in FY25 visit to ensure IC's are being met | potential site visit in FY25 visit to ensure IC's are being met | potential site visit in FY25 visit to ensure IC's are being met
Will site be suitable for Unrestricted use after Closure. | NO | NO | NO | NO | NO
Is there an IC in place? | YES | YES | YES | YES | YES
Type of IC | Advance approval required to transport soil or groundwater off-site., Excavation / Soil Movement Restrictions | Advance approval required to transport soil or groundwater off-site. Groundwater Use Restrictions: No groundwater wells shall be installed on the contaminated area of the Site without prior DEC approval.Groundwater Use Restrictions New Construction Restrictions, Subdivision Restriction | Recorded Deed Notice- Notice of Environmental Contamination; Excavation and Soil movment restrictions; contaminated soil remediation should occur once accessible (when USTs are removed); groundwater monitoring ceased in 2018. | Groundwater use restrictions; New construction restrictions; Excavation / soil restrictions; Subdivision restriction; Movement or use of contaminated soil (including onsite) restricted. When contaminated soil is acessible, Remediation should occur | Capped : Maintenance / Inspection Of Engineering Controls & Advance approval required to transport soil or groundwater off-site.

## Sites Not Listed on ADEC
SITE | Mink Creek | Moose Creek RR Pilings | Matanuska River Dump | Dump at the Old Dykes by Matanuska River | Dump Below 3 Bears on N. Birchwood Loop Rd. | Lazy Mountain Barrel Dump
BACKGROUND | Lorretta French Complex is a dump site and former Landfill. There is potential leaching from this site to Mink Creek | Land was used by the AK Railroad. Creosote pilings that supported the train tracks are leftover adjacent to the confluence of Moose Creek and the Matanuska River. 30-50 creosote pilings in groups, within 1/2 mi of eachother Some of these pilings are in contact with the river. | This is an open debris pile on and in the Matanuska River. The Alaska Railroad initially placed railroad cars at the site in the 1960’s to help stabilize the riverbank. After the railroad cars were placed, the site was used as an unpermitted open dump. | Tribal Member Concern that needs to be Investigated | A couple elders reported this as a dump site and mentioned "lots of cars were dumped there" | 10-15 55 gallon Drums on the top of the hill from access road to Lazy Mountain Trailhead. From SV Coordinator could read Diesel and Gear lube labels.
STATUS (Active/Closed) | Not Listed | Not Listed | Not Listed | Not Listed | Not Listed | Not Listed
SITE ADDRESS | 16515 CENTERFIELD DRIVE #100, Eagle River, 99577-7719 | Mouth of Moose Creek, Sutton AK, 99645 | 1/4 to 1/2 mile north of Eagle Ave. Palmer, 99645 | Palmer | N. Birchwood Loop Rd. Chugiak 99567 | Uphill Access Rd to TH can see from road, Palmer 99645
LATITUDE, LONGITUDE | 61.39615, -149.48717 | 61.673642, -149.039017 | 61.61715, -149.1062 | NA | NA (obtain this in future site visit) | NA
LANDOWNER | EI | EI owns surrounding land, but AK Railroad owns right of way for old tracks where contamination is located | City of Palmer (or on right of way) | NA | NA | NA
RP | Lorretta French Complex | DOD, AK Railroad. | AK Railroad | NA | NA | NA
ACREAGE | 0.64 acres | ~ 5 acres | NA | NA | NA | ~2 acres?
TYPE OF SITE (contamination) | Hazardous substances. Possible Petroleum leaching from Landfill | Hazardous Substances | Dump site: Petroleum and other water quality pollutants | Hazardous Substances: Dump site | Hazardous Substances: Dump site | Petroleum & potentially other hazardous contaminates
ADEC LINK | Not Listed | Not Listed | Not Listed | Not Listed | Not Listed | Not Listed
NVE's TRP HISTORY | NA | SV 8.25; | NVE debris assesment, 2004; SV 2020; SV 2022 | Tribal member concern that was reported to NVE, input in inventory (unknown time) | Tribal member concern that was reported to NVE, input in inventory (unknown time) | Site reported Via Brownfield tool; SV 2022
NVE's PREVIOUS ACTION (Coordinator) | Contacted by Office of Grant Development. EI got funding for Site assesments with MOA. EI & MOA will be using this funding to perform a Site Assesment. | Site visit with EI, Chickaloon TRP, Kyle Robillard and Knik Land Director. | Prioritized site to update on website. Report files are not valid and outdated. | Coordinator identified lack of information about this site and prioritized it for future Actions | Coordinator identified lack of information about this site and prioritized it for future Actions | Identified site with contractor to be investigated further.
DATE OF ACTION | 2025-09-19 | 2025-10-09 | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19
NVE's NEXT ACTION | Stay Involved with EI and any reports/information that comes from the assesment | Lead TRP for the site is in talks, for now site will sit and we will reapproach this again in the spring. | Good for a potential SV | SV and tracking down who reported/ any other information to locate it | SV | SV
Is there an IC in place or will it be suitable for Unrestricted use after Closure. | NO | NO | NO | NO | NO | NO
Type of IC | NA | NA | NA | NA | NA | NA

## Additional Resources
Additional Resources | More information about each site and the steps taken available on the Site Narrative document available on the NVE contaminated sites page.
ADEC Interactive Map
https://www.arcgis.com/apps/mapviewer/index.html?webmap=315240bfbaf84aa0b8272ad1cef3cad3
Information about the Tribal Response Program and its Funding Source
https://dec.alaska.gov/spar/csp/brownfields/tribal-response-program
If you see something, report it!
NVE has a Brownfield reporting tool available on the contaminated sites page.
https://docs.google.com/forms/d/1x-u0adrSf3RAv7E1QZZkoCvQTYfa5ybCVhArzG0uUsk/edit
Feel free to reach out with any questions or if you would like to report anything over the phone.
Kiana Donat: Tribal Response Program Coordinator
kdonat@eklutna.org
907-390-9003
Natalie Velez: Land and Environment Director
nvelez@eklutna.org
907-691-4843